# SPECIAL CONDITIONS

# CONTENTS

These conditions amplify and supplement, if necessary, the General Conditions governing the Contract. Unless the Special Conditions provide otherwise, those General Conditions remain fully applicable. The numbering of the Articles of the Special Conditions is not consecutive but follows the numbering of the Articles of the General Conditions. In exceptional cases, and with the authorisation of the appropriate Commission departments, other clauses may be added to cover specific situations.

Article 2	Language of the Contract

2.1	The language used shall be English.

Article 4	Communications

4.1	For the Contracting Authority

| Name: | Jovan Nešović |
| --- | --- |
| Address: | Cara Lazara 52A, 36000 Kraljevo |
| Fax: | / |
| e-mail: | javor@ptt.rs |

For the Contractor:

< To be introduced at contracting stage>

Article 7	Supply of documents

Together with the delivery the Contractor shall supply:

- Technical documentation, instruction (installation, operation and regular maintenance) Manuals in serbian,

- Warranty certificate

- Invoice;

Article 8	Assistance with local regulations

Whilst the Contracting Authority agrees to use its contacts with the authorities where appropriate to assist the Contractor in obtaining the required permits or import licences, the prime and ultimate responsibility for the obtaining of these and licences shall lie with the Contractor who shall keep the Project Coordinator informed.

If the Contractor is late in applying for or fails to apply for such permits or licences then it may not claim for extension in the Period of Execution or additional costs as a result.

Article 9	General Obligations

9.9	Contractor must to comply with its minimum obligation toward visibility. These activities must comply with the rules lay down in the Communication and Visibility Manual for EU External Actions published on the EuropeAid Website: https://ec.europa.eu/europeaid/funding/communication-and-visibility-manual-eu-external-actions_en .

Article 11	Performance guarantee

11.1	Performance guarantee is not required.

Article 12	Liabilities and Insurance

12.1. a)	By derogation from Article 12.1. a) paragraph 2, of the General Conditions, compensation for damage to the supplies resulting from the Contractor's liability in respect of the Contracting Authority is capped at an amount equal to the contract value.

12.1. b)	By derogation from Article 12.1. b), paragraph 2, of the General Conditions, compensation for damage resulting from the Contractor's liability in respect of the Contracting Authority is capped at an amount equal to the contract value.

12.2. a) By derogation from Article 12.2, a), paragraph 2 of the General Conditions it is, if requested, within 5 days, that the Contractor shall provide the Contracting Authority with all cover notes and/or insurance certificates showing that the Contractor's obligations relating to insurance are fully respected.

Article 13	Programme of implementation of tasks

13.2	Delivery, installation and commissioning of the supplies to the place of acceptance shall be finalised within 60 calendar days from contract signature by both parties.

Article 14	Contractor’s drawings

14.1	Contractor will submit Manuals and drawings related to each item of supplies as provided by the producer or, if required, by the Serbian law.

These Manuals and drawings will be submitted at least with the delivery of supplies.

Article 15	Sufficiency of tender prices

15.1	The prices in the contract are fixed and not subject to any revision.

Article 16	Tax and customs arrangements

16.1	Delivery conditions are DDP as mentioned in the GC. For supplies manufactured locally, all domestic fiscal charges applicable to their manufacture, including VAT, shall be excluded.

For supplies to be imported into the country of the Contracting Authority, all duties and taxes applicable to their importation, including VAT shall be excluded.

Whatever the origin of the supplies, the contract shall be exempt from stamp and registration duties.

Article 17	Patents and licences

17.1	Not applicable.

Article 18	Commencement order

18.1	The implementation of the tasks shall start on the date of contract signature by both parties.

Article 19	Period of implementation of the tasks

19.1	The period of implementation of the tasks of the contractor shall be 20 calendar days from the commencement date.

Article 24	Quality of supplies

24.2	No preliminary technical acceptance is required.

Article 25	Inspection and testing

25.2	The inspection and testing prior to the acceptance will take place at the locations where the goods are delivered. During the inspection and testing procedure, technical performances, the technical specifications, and technical documentation will be verified.

Article 26	General principles for payments

26.1	Payments shall be made in RSD. The exchange rate to be used for payment shall be InforEuro exchange rate for the month when the tender is launched

Payments shall be authorised and made by Legal Representative of Contracting authority.

26.3	By derogation, the final payment to the Contractor of the amounts due shall be made within 90 days after receipt by the Contracting Authority of an invoice and of the application for the certificate of provisional acceptance.]

26.5	In order to obtain payments, the Contractor must forward to the authority referred to in paragraph 26.1 above:

- For the 100 % balance, the invoice(s) in triplicate together with the request for final acceptance of the supplies. No pre-financing is possible.

Article 28	Delayed payments

28.2	By derogation from Article 28.2 of the General Conditions, once the deadline laid down in Article 26.3 has expired, the Contractor shall, upon demand, be entitled to late-payment interest at the rate and for the period mentioned in the General Conditions. The demand must be submitted within two months of receiving late payment.

Article 29	Delivery

29.3	The packaging shall become the property of the recipient subject to environmental considerations.

Article 31	Provisional acceptance

The Certificate of Provisional Acceptance must be issued using the template in Annex C11.

Article 32	Warranty obligations

32.6	Where the commercial warranty issued by the manufacturer of a particular item/product is longer than the below mentioned warranty of two years after final acceptance, the Contractor will deliver the related certificates/documents to the Beneficiary and will provide complete support to the Beneficiary in contacting the manufacturer.

32.7	The warranty must remain valid for minimum 10 years for solar panels and 2 years for inverter and executed works after provisional acceptance.

Article 33	After-sales service

33.1	Not Applicable.

Article 40	Settlement of disputes

40.4	Any disputes arising out of or relating to this Contract which cannot be settled otherwise shall be referred to the exclusive jurisdiction of relevant court of law in Republic of Serbia accordance with the national legislation of the state of the Contracting Authority.

* * *